Clerks Report 25.01.2023

Item	Date	Action
Severn Trent and Cotwalton Junction to B5066 ref: 4181743 & 4237100 - Missing bollards. 25.05.22 – still chasing	18.12.20	Monitor
Hedge cutting – Farm Lea, letters have been sent to all the residents / 25.05.22 – still chasing	02.02.21	Monitor
Hedge cutting – 2 Farm Lea, pictures have been taken and sent to Stafford Rural Homes to investigate. – Chased with Stafford rural homes on 29.09.21 - no update yet. – clerk to chase – 29.10.21 – chased again – Clerk to forward information to Cllr J Davies to see if he may be able to push them as well. – Information has been passed to Cllr J Davies. – Cllr Davies has emailed. – 23.03.22 no further information has been received. Cllr J Davis will chase. – 27.04.22 – Cllr J Davies still chasing. 25.05.22 – still chasing – 22.06.22 – this issue has now been passed to Stafford Rural Homes Legal department to advise. – 20.07.22, advised by Homes Plus the footpath and hedge is outside the property boundary and therefore not the property owners’ responsibility. Clerk to report to Stafford County Council to trim back the hedges. 28.09.2022 Homes plus reported it’s not their responsibility, CC reported it’s not their responsibility. Next step to contact Accord Housing – Cllr PD will supply clerk with contact details. – 23.11.22 Clerk to request TGM to issue a quote to cut this section.	02.02.21	Monitor
White lines – Cotwalton Junction to B5066 23.02.22 – Clerk to report again, reporting a serious RTA which took place during December 2021 caused by drivers not keeping to the right side of the road. Clerk to extend from Spotgate to Junction B5066. Reported / 23.03.22 – No further information has been received 25.05.22 – still chasing – 28.09.2022 – still to be resolved – RESOLVED October 2022	21.07.21	RESOLVED
Hedges – Hill Farm house and The Old Byer. Letter sent to both properties requesting the hedge cut back to the original boundary. / 23.03.22 – Report to highways, they are now obstructing the road. – 27.04.22 Clerk to send a letter advising the owners legal responsibility. 15.05.22 – The hedge has now been cut back to the original boundary – 25.05.22, location has now been established and the clerk will send a letter to the residents.	22.09.21	Monitor
Severn Trent Gate / Still has not been replaced – Cllr Woodward will see if she can obtain a contact from her source – clerk to write a letter – Severn Trent have been advised. – No further information has been received. 25.05.22 job number for Seven Trent to repair the gateway, 2005645554		Monitor
Erosion of bank opposite church buildout / Clerk has reported to highways, believed due to wide vehicles using the road churning up the curb side. Children are having to walk in it, and it could potentially block the drains. / 23.03.22 – No further information has been received.	23.02.22	Monitor
Road sign by Roebuck, this has been reported ref number - 4281637	13.05.22	Monitor
30mph road sign on Creswell Road by new SID’s – this has been reported, ref number - 4281636	13.05.22	Monitor
Footpath 14, report to SCC – ROW ref: 220730332	20.07.22	Monitor
Missing bollard – Road narrowing site by Roebuck Pub – ref 4288799 / Someone has stuck the two bollards together, obstructing the hi vis section on the bollard. Clerk to report.	20.07.22	Monitor
Drain – Dingle Lane – original works reference 4288044	26.10.22	Monitor
Water spring, by buildout on Roebuck Bank. Concern has been raised, when temperature drops this will cause ice on the roads causing danger to vehicles. Needs reporting before anything happens. – ref 4298332	26.10.22	Monitor
Missing road sign, approaching Hilderstone crossroads from the village – ref 4291120	08.2022	Monitor
Broken kerb & footpath on Roebuck Hill. - 4299610	17.11.22	Monitor
Dingle Lane junction – Drain is sunken and dangerous clerk to report	23.11.22	Clerk
Play area, wetpour has shrunk and is now causing trip hazard, clerk to report to Stafford Borough Council.	23.11.22	Clerk